Planning Report

Deliverable C

Acme-Starters

## Planning

This chapter presents the tasks performed to fulfil the requirements of Deliverable C, including Requirement Zero and the Student Specific Requirements defined in the Level C specification.

### Task Listing

| Title | Description | Assignee(s) & Role(s) | Planned Time (h) | Actual Time (h) |
| --- | --- | --- | --- | --- |
| Repository Setup | GitHub repository creation and configuration of project structure. | Student 1 – Manager | 2 | 2 |
| Starter Project Instantiation | Adaptation of “Hello-World” into “Acme-Starters-C” including branding. | Student 1 – Developer | 4 | 4 |
| Requirements Analysis | Review and interpretation of Level C requirements and domain models C01–C05. | Student 4 – Analyst | 6 | 6 |
| Administrator Seed Data | Creation of required administrator accounts. | Student 2 – Developer | 2 | 2 |
| Model-CG Constraints | Implementation of structural and relational constraints. | Student 2 & 3 – Developers | 8 | 9 |
| Student C01 Implementation | Inventions and Inventor role implementation. | Student 1 – Developer | 8 | 8 |
| Student C02 Implementation | Campaigns and Spokesperson implementation. | Student 2 – Developer | 8 | 8 |
| Student C03 Implementation | Strategies and Fundraiser implementation. | Student 3 – Developer | 8 | 8 |
| Student C04 Implementation | Sponsorships and Sponsor implementation. | Student 4 – Developer | 8 | 8 |
| Student C05 Implementation | Audit reports and Auditor implementation. | Student 5 – Developer | 8 | 8 |
| Testing Data Creation | Creation of mandatory sample users and role data. | All – Testers | 6 | 7 |
| Clean Environment Validation | Testing deliverable from EV in clean environment. | Student 1 & 4 – Testers | 4 | 4 |
| Planning Report | Preparation of planning, budget and progress chapters. | Student 1 – Manager | 6 | 6 |

## Budget

### Estimated Cost

Estimated Hours per Role

| Role | Estimated Hours |
| --- | --- |
| Project Manager | 8 |
| Developers (5) | 48 |
| Analyst | 6 |
| Testers | 10 |

Total Estimated Hours: 72 hours

Personnel Cost Estimation

academic hourly rates considered:

- Project Manager: 30 €/h

- Developer: 25 €/h

- Analyst: 20 €/h

- Tester: 20 €/h

| Role | Hours | Rate | Cost (€) |
| --- | --- | --- | --- |
| Manager | 8 | 30 | 240 |
| Analyst | 6 | 28 | 168 |
| Developers | 48 | 25 | 1,200 |
| Testers | 10 | 20 | 200 |

Total estimated personnel cost: 1.808 €

Amortisation Cost

Each team member used a laptop valued at 1,500 €.

Linear amortisation over three years:

1,500 € / 3 = 500 € per year

Assuming three weeks of development:

500 € / 52 ≈ 9.6 € per week

9.6 × 3 ≈ 29 €

For five students:

29 € × 5 ≈ 145 €

Estimated amortisation cost: 145 €

Total Estimated Cost

Personnel: 1.808 €

Amortisation: 145 €

Total estimated cost: 1.923 €

### Actual Cost

Actual Hours:

| Role | Actual Hours |
| --- | --- |
| Manager | 8 |
| Analyst | 6 |
| Developers | 50 |
| Testers | 11 |

Total actual hours: 75 hours

Actual Personnel Cost

| Role | Hours | Rate | Cost (€) |
| --- | --- | --- | --- |
| Manager | 8 | 30 | 240 |
| Analyst | 6 | 28 | 168 |
| Developers | 50 | 25 | 1,250 |
| Testers | 11 | 20 | 220 |

Total actual personnel cost: 1.878 €

Amortisation unchanged: 145 €

Total actual cost: 2.023 €

Deviation Analysis

The deviation was mainly due to additional effort required to correctly enforce publishing constraints and ensure non-modifiability of published entities, as required by the Level C functional specifications.

The derivation is moderate and within acceptable academic project margins.

## Progress

### Progress Records

Performance indicators defined in the Charter:

- Task completion within planned time

- Compliance with assigned responsibilities

- Participation in testing activities

| Member | Indicator Result | Good/Bad | Action Taken |
| --- | --- | --- | --- |
| Student 1 | All managerial and development tasks delivered on time | Good | Positive feedback |
| Student 2 | Minor delay in constraint implementation | Good | Additional coordination session |
| Student 3 | Tasks completed within expected timeframe | Good | No action required |
| Student 4 | Analysis completed correctly and supported development | Good | Recognition during meeting |
| Student 5 | Implementation delivered on time | Good | No action required |

Overall team performance is considered satisfactory.

### Conflict Management

A minor coordination conflict arose during the interpretation of certain relational constraints and publishing rules. The Analyst clarified the intended behaviour according to the domain models, and responsibilities were redistributed accordingly.

No severe conflicts occurred and no disciplinary measures were required.